## Visual Project Charter
Cartify Mobile Checkout Redesign
This is a filled example based on a sample eCommerce project, showing how the blank template looks once completed.
Sponsor |  | PM / TPM |  | Version |  | Target Completion
Sarah Chen, VP of Product |  | Jordan Lee, TPM |  | v1.2 |  | 2026-04-15
Executive Snapshot
OBJECTIVE |  | BUSINESS CASE |  | BUDGET ENVELOPE |  | CONTINGENCY
Cut mobile cart abandonment 25% with a streamlined checkout |  | Mobile drop-off costs ~$2.1M in lost revenue yearly |  | $180,000 |  | 15%
Milestone Timeline
Project Start Date | 2026-01-05
Milestone | Owner | Start Date | Finish Date | Status
Discovery & UX Research Complete | Priya Nair (UX Lead) | 2026-01-05 | 2026-01-18 | Green
Checkout Flow Design Sign-off | Marcus Webb (Design Lead) | 2026-01-19 | 2026-02-01 | Green
Payment Gateway Integration Complete | Elena Rodriguez (Backend Lead) | 2026-02-02 | 2026-02-22 | Amber
QA & Cross-Browser Testing Complete | Devon Park (QA Lead) | 2026-02-23 | 2026-03-08 | Amber
Go-Live (Phased Rollout) | Jordan Lee (TPM) | 2026-03-09 | 2026-03-22 | Green
Timeline note: the visual bars below reflect the Start/Finish dates above, in weeks from the Project Start Date.
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Discovery & UX Research Complete
Checkout Flow Design Sign-off | bar: W3 to W4
Payment Gateway Integration Complete
QA & Cross-Browser Testing Complete | bar: W8 to W9
Go-Live (Phased Rollout)
Scope at a Glance
IN SCOPE | W4: OUT OF SCOPE
✅ Redesigned one-page mobile checkout UI | W4: 🚫 Desktop checkout redesign
✅ Apple Pay & Google Pay integration | W4: 🚫 Loyalty points redemption at checkout
✅ Real-time shipping cost calculator | W4: 🚫 Multi-currency support
✅ Guest checkout flow | W4: 🚫 Subscription / recurring billing
Stakeholder Map (RACI)
Stakeholder / Role | W1: Name; W2: RACI; W3: Cadence; W4: Escalation
Executive Sponsor | W1: Sarah Chen; W2: A; W3: Monthly; W4: CTO
Product Owner | W1: Marcus Webb; W2: R; W3: Weekly; W4: Jordan Lee
Technical Lead | W1: Elena Rodriguez; W2: R; W3: Weekly; W4: Jordan Lee
Security / Compliance | W1: David Kim; W2: C; W3: As needed; W4: Sarah Chen
RACI key: R = Responsible, A = Accountable, C = Consulted, I = Informed
Risk Register
Severity | W1: Risk; W2: Owner; W3: Mitigation
High | W1: Payment gateway API rate limits under peak load; W2: Elena Rodriguez; W3: Load testing scheduled pre-launch; secondary gateway identified as fallback
Medium | W1: Safari/iOS checkout has historically shown rendering bugs; W2: Devon Park; W3: Dedicated Safari/iOS regression pass added to QA cycle
Low | W1: Launch window overlaps with early holiday traffic increase; W2: Jordan Lee; W3: Rollout phased to 10% of traffic before full release
Technical Readiness (TPM Focus)
Technical Area | W1: Decision; W2: Owner; W3: Status
Infrastructure / Platform | W1: Scale checkout service via Kubernetes autoscaling; W2: Elena Rodriguez; W3: Green
Security / Compliance | W1: PCI-DSS SAQ A-EP revalidation before launch; W2: David Kim; W3: Amber
Data / Integration | W1: Real-time inventory sync via existing order service; W2: Priya Nair; W3: Green