## Visual Project Charter
[Project Name]
How to use: fill in the white cells only. Short phrases work better than full sentences, this charter is designed to be scanned, not read.
Sponsor |  | PM / TPM |  | Version |  | Target Completion
[Name] |  | [Name] |  | v1.0 |  | [Date]
Executive Snapshot
OBJECTIVE |  | BUSINESS CASE |  | BUDGET ENVELOPE |  | CONTINGENCY
[One-line goal] |  | [Why now, in one line] |  | [Amount] |  | [Reserve %]
Milestone Timeline
Project Start Date | 2026-01-01
Milestone | Owner | Start Date | Finish Date | Status
Discovery & Planning Complete | [Owner] | 2026-01-01 | 2026-01-14 | Green
Design Sign-off | [Owner] | 2026-01-15 | 2026-01-28 | Green
Core Build Complete | [Owner] | 2026-01-29 | 2026-02-25 | Amber
QA & UAT Complete | [Owner] | 2026-02-26 | 2026-03-11 | [Green/Amber/Red]
Go-Live | [Owner] | 2026-03-12 | 2026-03-18 | [Green/Amber/Red]
Timeline note: the visual bars below reflect the Start/Finish dates above, in weeks from the Project Start Date. If you change milestone dates, shift the colored cells in the grid to match.
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Discovery & Planning Complete
Design Sign-off | bar: W3 to W4
Core Build Complete
QA & UAT Complete | bar: W9 to W10
Go-Live
Scope at a Glance
IN SCOPE | W4: OUT OF SCOPE
✅ [Deliverable / feature] | W4: 🚫 [Excluded item]
✅ [Deliverable / feature] | W4: 🚫 [Excluded item]
✅ [Deliverable / feature] | W4: 🚫 [Excluded item]
✅ [Deliverable / feature] | W4: 🚫 [Excluded item]
Stakeholder Map (RACI)
Stakeholder / Role | W1: Name; W2: RACI; W3: Cadence; W4: Escalation
Executive Sponsor | W1: [Name]; W2: A; W3: Monthly; W4: [Name]
Product Owner | W1: [Name]; W2: R; W3: Weekly; W4: [Name]
Technical Lead | W1: [Name]; W2: R; W3: Weekly; W4: [Name]
Security / Compliance | W1: [Name]; W2: C; W3: As needed; W4: [Name]
RACI key: R = Responsible, A = Accountable, C = Consulted, I = Informed
Risk Register
Severity | W1: Risk; W2: Owner; W3: Mitigation
High | W1: [Risk description]; W2: [Owner]; W3: [Mitigation plan]
Medium | W1: [Risk description]; W2: [Owner]; W3: [Mitigation plan]
Low | W1: [Risk description]; W2: [Owner]; W3: [Mitigation plan]
Technical Readiness (TPM Focus)
Technical Area | W1: Decision; W2: Owner; W3: Status
[Infrastructure / Platform] | W1: [Decision]; W2: [Owner]; W3: Green
[Security / Compliance] | W1: [Decision]; W2: [Owner]; W3: [Green/Amber/Red]
[Data / Integration] | W1: [Decision]; W2: [Owner]; W3: [Green/Amber/Red]